## README
SUPPLY CHAIN CONTROL TOWER
Synthetic Data — live export
Source | Pulled live from the running API across all 3 tenants. Reflects the seed code in app/sample_data.py + app/planning.py + fixtures/hydro/.
Tenants | arcforge (Power Systems EPC) · helios (Offshore Engineering) · northwind (Heavy Engineering). Rows are tinted by tenant.
Isolation | Each tenant's data is fully scoped — these rows are what that tenant actually sees via its own token.
Sheets | Projects · BOM (every line, all projects) · Vendors · Concentration · PRs · POs · Commercial · Approvals · Alerts.
Seeded counts | arcforge: 4 projects / 50 BOM lines / 7 vendors · helios: 4 projects / 23 BOM lines / 4 vendors · northwind: 4 projects / 89 BOM lines / 4 vendors

## Projects
PORTFOLIO
Projects
Tenant | Project ID | Name | Client | Site | Sector | Start | Milestones | BOM lines | Completion % | MS passed | BOM delivered | BOM budget $
arcforge | PRJ-RB-660 | Riverbank 2x660 MW Power Plant | Arcforge Power | Riverbank, Gujarat | Power EPC | 2026-01-22 | 4 | 17 | 22.4 | 0 | 5 | 14748980
arcforge | PRJ-AF-CCGT | Tanjore Combined-Cycle Gas Plant 750 MW | Arcforge Power | Tanjore, Tamil Nadu | Power EPC | 2026-04-22 | 3 | 14 | 2.9 | 0 | 1 | 20106299
arcforge | PRJ-AF-SUB | Sundarpur 765 kV Substation Upgrade | Arcforge Grid | Sundarpur, Madhya Pradesh | Transmission EPC | 2026-04-22 | 3 | 10 | 0 | 0 | 0 | 20628000
arcforge | PRJ-AF-MERIDIAN | Meridian 2x350 MW CCGT — Unit 1 Execution | Arcforge Power | Meridian, Andhra Pradesh | Power EPC | 2025-04-17 | 5 | 9 | 55.6 | 2 | 5 | 20196000
helios | PRJ-NS-OSS | North Sea Offshore Substation | Helios Offshore Operations | Aberdeen, UK | Offshore Engineering | 2026-03-23 | 3 | 4 | 0 | 0 | 0 | 11728000
helios | PRJ-HE-WIND | Dogger Bank Offshore Wind 480 MW | Helios Renewables | Dogger Bank, North Sea | Offshore Wind EPC | 2026-04-22 | 3 | 5 | 0 | 0 | 0 | 709778400
helios | PRJ-HE-FPSO | Hawthorn FPSO Topsides | Helios Upstream | West of Shetland | Offshore Oil & Gas EPC | 2026-04-22 | 3 | 5 | 0 | 0 | 0 | 42200000
helios | PRJ-HE-VALHALL | Valhall Bravo Platform Tie-In | Helios Upstream | Valhall Field, North Sea | Offshore Oil & Gas EPC | 2025-04-17 | 5 | 9 | 55.5 | 2 | 5 | 20346000
northwind | HYD-MAHADEV-220 | Mahadev Hydro 220 MW (2x110) | Northern Hills Power Corporation | Sutlej Basin, Himachal Pradesh, IN | Hydropower EPC | 2025-04-01 | 12 | 70 | 16.7 | 5 | 0 | 78603600
northwind | PRJ-NW-STEEL | Polaris Steel Rolling Mill Modernization | Polaris Steel | Jamshedpur, Jharkhand | Heavy Industry EPC | 2026-04-22 | 3 | 5 | 0 | 0 | 0 | 32120000
northwind | PRJ-NW-CEMENT | Granite Ridge Cement Line 2 | Granite Ridge Cement | Chandrapur, Maharashtra | Heavy Industry EPC | 2026-04-22 | 3 | 5 | 0 | 0 | 0 | 20460000
northwind | PRJ-NW-KAVI | Kavi Hydro Unit 3 Major Overhaul | Northern Hills Power Corporation | Kavi, Himachal Pradesh | Hydropower EPC | 2025-04-17 | 5 | 9 | 52.5 | 2 | 5 | 8156000

## BOM
BOM
Bill of Materials — 162 lines
Tenant | Project | Item ID | Code | Description | Category | Qty | UoM | Unit cost $ | Supplier | Lead (d) | Need by | Milestone | Status
arcforge | PRJ-RB-660 | RB-001 | BFP-660-A | Boiler Feed Pump 660MW set A | Rotating equipment | 2 | EA | 920000 | Helios Cast & Forge | 240 | 2026-09-19 | M3 | planned
arcforge | PRJ-RB-660 | RB-002 | VALVE-16-A105 | 16 inch forged gate valve | Forged valves | 30 | EA | 3850 | Helios Cast & Forge | 95 | 2026-08-20 | M3 | ordered
arcforge | PRJ-RB-660 | RB-003 | PLC-S7-IO48 | PLC I/O module 48 point | Automation | 16 | EA | 2250 | BluePeak Controls | 55 | 2026-07-31 | M2 | spec_missing
arcforge | PRJ-RB-660 | RB-004 | TXF-110-40 | Auxiliary transformer 110/11 kV 40 MVA | Electrical | 1 | EA | 480000 |  | 180 | 2026-08-30 | M3 | spec_missing
arcforge | PRJ-RB-660 | RB-005 | BUSBAR-CU-40 | Copper busbar 40 mm | Electrical | 140 | M | 92 | Copperline Metals | 28 | 2026-07-26 | M2 | planned
arcforge | PRJ-RB-660 | RB-006 | STRUCT-S355 | Structural steel S355 fabrication | Fabrication | 220 | T | 1850 |  | 60 | 2026-08-10 | M3 | planned
arcforge | PRJ-RB-660 | RB-007 | COND-TUBE-INC | Condenser tubes Inconel 625 | Tubing | 4200 | M | 48 |  | 150 | 2026-09-09 | M3 | spec_missing
arcforge | PRJ-RB-660 | RB-008 | COOLING-TWR-MOD | Induced draft cooling tower module | Cooling | 4 | EA | 310000 |  | 210 | 2026-11-18 | M4 | planned
arcforge | PRJ-RB-660 | PRJ-RB-660-U0002 | RB-EXEC-001 | Boiler ID fan assembly (received) | Rotating equipment | 2 | EA | 420000 | Helios Cast & Forge | 180 | 2026-06-30 | M2 | delivered
arcforge | PRJ-RB-660 | PRJ-RB-660-U0003 | RB-EXEC-002 | Coal mill rollers (received) | Rotating equipment | 8 | EA | 180000 | Helios Cast & Forge | 150 | 2026-07-15 | M2 | delivered
arcforge | PRJ-RB-660 | PRJ-RB-660-U0004 | RB-EXEC-003 | Air preheater bundle (received) | Heat recovery | 2 | EA | 890000 | Kerala Forge Works | 210 | 2026-07-30 | M2 | delivered
arcforge | PRJ-RB-660 | PRJ-RB-660-U0005 | RB-EXEC-004 | Generator step-up transformer (received) | Electrical | 2 | EA | 1100000 | BluePeak Controls | 300 | 2026-08-15 | M3 | delivered
arcforge | PRJ-RB-660 | PRJ-RB-660-U0006 | RB-EXEC-005 | Cooling tower fill bulk (received) | Cooling | 12 | EA | 68000 | Copperline Metals | 90 | 2026-08-30 | M2 | delivered
arcforge | PRJ-RB-660 | PRJ-RB-660-U0007 | RB-EXEC-006 | Vacuum deaerator + tank (ordered) | Process | 1 | EA | 640000 | Kerala Forge Works | 180 | 2026-10-30 | M3 | ordered
arcforge | PRJ-RB-660 | PRJ-RB-660-U0008 | RB-EXEC-007 | FGD scrubber slurry pumps (planned) | Rotating equipment | 4 | EA | 320000 | Helios Cast & Forge | 150 | 2026-11-30 | M3 | planned
arcforge | PRJ-RB-660 | PRJ-RB-660-U0009 | RB-EXEC-008 | Ash handling vessels (planned) | Process | 4 | EA | 210000 |  | 180 | 2026-12-15 | M4 | planned
arcforge | PRJ-RB-660 | PRJ-RB-660-U0010 | RB-EXEC-009 | Generator excitation system (planned) | Electrical | 1 | LOT | 580000 | BluePeak Controls | 150 | 2027-01-15 | M4 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-001 | GT-9F-FRAME | Gas turbine 9F frame unit | Rotating equipment | 2 | EA | 4200000 | Helios Cast & Forge | 365 | 2026-11-20 | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-002 | HRSG-3P-RH | Triple-pressure HRSG with reheat | Heat recovery | 2 | EA | 2800000 |  | 300 | 2026-10-19 | M3 | spec_missing
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-003 | STG-250 | Steam turbine generator 250 MW | Rotating equipment | 1 | EA | 3100000 | Helios Cast & Forge | 330 | 2026-11-03 | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-004 | GSU-XFMR-420 | Generator step-up transformer 420 MVA | Electrical | 2 | EA | 880000 |  | 240 | 2026-09-19 | M2 | spec_missing
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-005 | DCS-CONTROL | Distributed control system | Automation | 1 | LOT | 1200000 | BluePeak Controls | 120 | 2026-07-21 | M2 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0002 | EDGE-OK-01 | Healthy row for control | Electrical | 4 | EA | 1200 | Copperline Metals | 60 | 2026-09-30 | M2 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0006 | EDGE-NEGQTY | Negative quantity | Electrical | -3 | EA | 500 | Copperline Metals |  |  | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0007 | EDGE-BADCOST | Bad unit cost | Electrical | 4 | EA |  | Copperline Metals |  |  | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0008 | EDGE-BADDATE | Bad need-by date | Electrical | 4 | EA | 500 | Copperline Metals | 30 |  | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0009 | EDGE-BADSTATUS | Unknown status (should warn + default) | Electrical | 4 | EA | 500 | Copperline Metals | 30 | 2026-09-30 | M3 | spec_missing
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0010 | EDGE-BADLEAD | Bad long-lead days | Electrical | 4 | EA | 500 | Copperline Metals |  | 2026-09-30 | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0011 | EDGE-OK-02 | Quoted, contains, commas | Electrical | 12 | EA | 2000 | Copperline Metals | 45 | 2026-09-30 | M3 | planned
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0012 | EDGE-OK-03 | Unicode é ñ 中 — long desc shouldn't break the upload | Process | 1 | EA | 9999 | Helios Cast & Forge | 90 | 2026-10-15 | M3 | delivered
arcforge | PRJ-AF-CCGT | PRJ-AF-CCGT-U0013 | EDGE-OK-04 | Status normalised to lower-case | Process | 2 | EA | 1500 |  | 30 | 2026-09-30 | M2 | ordered
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-001 | GIS-765 | 765 kV gas-insulated switchgear bay | Electrical | 6 | EA | 1450000 | BluePeak Controls | 280 | 2026-10-09 | M2 | planned
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-002 | ICT-1000 | Interconnecting transformer 1000 MVA | Electrical | 3 | EA | 2600000 |  | 320 | 2026-10-29 | M2 | spec_missing
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-003 | REACTOR-330 | Shunt reactor 330 MVAr | Electrical | 3 | EA | 980000 | Copperline Metals | 210 | 2026-09-04 | M2 | planned
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-004 | BUSBAR-ACSR | ACSR bundled conductor | Electrical | 18 | KM | 42000 | Copperline Metals | 60 | 2026-06-21 | M3 | planned
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-005 | PROT-RELAY | Numerical protection relay panel | Automation | 24 | EA | 18000 | Mitsuba Automation | 90 | 2026-07-06 | M3 | planned
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-U0002 | MIN-001 | Minimal-fields row 1 |  | 4 | EA | [5 empty] | spec_missing
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-U0003 | MIN-002 | Minimal-fields row 2 |  | 12 | EA | [5 empty] | spec_missing
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-U0004 | MIN-003 | Minimal-fields row 3 — proves required-only path |  | 1 | EA | [5 empty] | spec_missing
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-U0005 | MIN-004 | Minimal-fields row 4 |  | 80 | EA | [5 empty] | spec_missing
arcforge | PRJ-AF-SUB | PRJ-AF-SUB-U0006 | MIN-005 | Minimal-fields row 5 — no optional cols at all |  | 2 | EA | [5 empty] | spec_missing
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-001 | GT-7HA-CORE | Gas turbine 7HA core | Rotating equipment | 2 | EA | 3800000 | Helios Cast & Forge | 365 | 2026-11-03 | M2 | delivered
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-002 | HRSG-MOD-A | HRSG pressure modules | Heat recovery | 4 | EA | 1200000 | Helios Cast & Forge | 300 | 2026-08-30 | M3 | delivered
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-003 | COND-SHELL | Surface condenser shell | Process | 1 | EA | 980000 | Kerala Forge Works | 210 | 2026-06-01 | M3 | delivered
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-004 | FW-PUMP-MV | Boiler feed pump + MV motor | Rotating equipment | 3 | EA | 540000 | Helios Cast & Forge | 180 | 2026-05-02 | M3 | delivered
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-005 | CABLE-MV-TRAY | MV cable + tray bulk | Electrical | 12 | KM | 88000 | Copperline Metals | 60 | 2026-01-02 | M3 | delivered
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-006 | GSU-XFMR-300 | Generator step-up transformer 300 MVA | Electrical | 2 | EA | 760000 | BluePeak Controls | 240 | 2026-07-01 | M4 | ordered
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-007 | DCS-MERIDIAN | DCS + field instrumentation | Automation | 1 | LOT | 1100000 | BluePeak Controls | 120 | 2026-03-03 | M4 | spec_missing
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-008 | STACK-CEMS | Stack + CEMS package | Environmental | 2 | EA | 420000 |  | 150 | 2026-04-02 | M4 | spec_missing
arcforge | PRJ-AF-MERIDIAN | PRJ-AF-MERIDIAN-009 | AUX-COOLING | Auxiliary cooling water system | Cooling | 1 | LOT | 680000 | Mitsuba Automation | 90 | 2026-02-01 | M5 | spec_missing
helios | PRJ-NS-OSS | NS-001 | SWG-33-GIS | Gas-insulated switchgear 33kV | Electrical | 2 | EA | 640000 | BluePeak Controls | 200 | 2026-10-09 | M3 | spec_missing
helios | PRJ-NS-OSS | NS-002 | CBL-66-SUBSEA | Subsea export cable 66kV XLPE | Cables | 28 | KM | 215000 |  | 320 | 2026-10-29 | M3 | planned
helios | PRJ-NS-OSS | NS-003 | JACKET-STEEL | Jacket fabrication carbon steel | Fabrication | 1 | EA | 4200000 |  | 180 | 2026-10-19 | M3 | spec_missing
helios | PRJ-NS-OSS | NS-004 | J-TUBE-SS | J-tube stainless 316L | Tubing | 6 | EA | 38000 | Copperline Metals | 65 | 2026-09-19 | M3 | planned
helios | PRJ-HE-WIND | PRJ-HE-WIND-001 | MONOPILE-XL | XL monopile foundation | Offshore structural | 32 | EA | 3400000 | Aberdeen Steel Fab | 300 | 2026-10-19 | M2 | planned
helios | PRJ-HE-WIND | PRJ-HE-WIND-002 | WTG-12MW | 12 MW offshore wind turbine | Rotating equipment | 40 | EA | 14500000 |  | 420 | 2026-12-18 | M3 | spec_missing
helios | PRJ-HE-WIND | PRJ-HE-WIND-003 | ARRAY-66KV | 66 kV inter-array cable | Subsea cables | 85 | KM | 220000 | NorthCable Subsea | 240 | 2026-09-19 | M3 | planned
helios | PRJ-HE-WIND | PRJ-HE-WIND-004 | TP-COATING | Transition piece marine coating | Marine epoxy | 32 | LOT | 64000 | Coastline Marine Coatings | 45 | 2026-06-13 | M2 | planned
helios | PRJ-HE-WIND | PRJ-HE-WIND-005 | ROV-WETMATE | ROV wet-mate connector set | ROV connectors | 48 | EA | 4800 | DeepDive ROV Systems | 84 | 2026-07-03 | M3 | planned
helios | PRJ-HE-FPSO | PRJ-HE-FPSO-001 | SEP-TRAIN | 3-phase separation train | Process | 2 | EA | 5600000 |  | 360 | 2026-11-18 | M2 | spec_missing
helios | PRJ-HE-FPSO | PRJ-HE-FPSO-002 | GASCOMP-CENT | Centrifugal gas compressor | Rotating equipment | 3 | EA | 4100000 | Aberdeen Steel Fab | 330 | 2026-11-03 | M2 | planned
helios | PRJ-HE-FPSO | PRJ-HE-FPSO-003 | SWIVEL-STACK | Fluid swivel stack | Process | 1 | EA | 7800000 |  | 400 | 2026-12-08 | M3 | spec_missing
helios | PRJ-HE-FPSO | PRJ-HE-FPSO-004 | FLARE-BOOM | Flare boom structure | Offshore structural | 1 | EA | 2200000 | Aberdeen Steel Fab | 180 | 2026-08-20 | M2 | planned
helios | PRJ-HE-FPSO | PRJ-HE-FPSO-005 | RISER-FLEX | Flexible production riser | Subsea cables | 6 | EA | 1450000 | NorthCable Subsea | 270 | 2026-10-04 | M3 | planned
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-001 | SUBSEA-MANIFOLD | Subsea production manifold | Process | 1 | EA | 4200000 | Aberdeen Steel Fab | 360 | 2026-10-29 | M2 | delivered
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-002 | UMBILICAL-STATIC | Static control umbilical | Subsea cables | 8 | KM | 310000 | NorthCable Subsea | 300 | 2026-08-30 | M3 | delivered
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-003 | XMAS-TREE-HT | High-temp subsea tree | Process | 2 | EA | 2600000 |  | 330 | 2026-09-29 | M3 | delivered
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-004 | ROV-TIEIN-KIT | ROV tie-in tooling kit | ROV connectors | 4 | EA | 185000 | DeepDive ROV Systems | 84 | 2026-01-26 | M3 | delivered
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-005 | COAT-SPLASH | Splash-zone coating package | Marine epoxy | 6 | LOT | 96000 | Coastline Marine Coatings | 45 | 2025-12-18 | M3 | delivered
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-006 | RISER-FLEX-DYN | Dynamic flexible riser | Subsea cables | 3 | EA | 1450000 | NorthCable Subsea | 270 | 2026-07-31 | M4 | ordered
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-007 | PIG-LAUNCHER | Subsea pig launcher | Process | 1 | EA | 720000 | Aberdeen Steel Fab | 150 | 2026-04-02 | M4 | spec_missing
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-008 | CP-ANODE-SLED | Cathodic protection anode sled | Offshore structural | 5 | EA | 64000 |  | 120 | 2026-03-03 | M4 | spec_missing
helios | PRJ-HE-VALHALL | PRJ-HE-VALHALL-009 | CTRL-MODULE-SC | Subsea control module | Automation | 2 | EA | 880000 | DeepDive ROV Systems | 180 | 2026-05-02 | M5 | spec_missing
northwind | HYD-MAHADEV-220 | HYD-HM-001 | HM-TR-RACK-01 | Intake trash rack assembly 80 sq.m | Hydromechanical | 2 | SET | 185000 | SLP Industries | 240 | 2025-09-15 | M02 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-002 | HM-INTGT-01 | Intake gate vertical lift 6.5x7.5 m | Hydromechanical | 2 | EA | 420000 | ISGEC Heavy Engineering | 365 | 2025-12-01 | M03 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-003 | HM-INTHST-01 | Intake gate hoist hydraulic 60 t | Hydromechanical | 2 | EA | 210000 | ISGEC Heavy Engineering | 240 | 2025-12-01 | M03 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-004 | HM-DIVGT-01 | Diversion tunnel slide gate 4 m sq | Hydromechanical | 1 | EA | 165000 | Texmaco Rail | 210 | 2025-09-15 | M02 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-005 | HM-PEN-PIPE | Penstock steel pipe 4.5 m dia 14 mm thk | Hydromechanical | 1500 | M | 4200 | Jindal SAW | 480 | 2026-08-15 | M06 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-006 | HM-PEN-SDL | Penstock saddle support fabricated | Hydromechanical | 18 | EA | 28500 | SLP Industries | 180 | 2026-07-15 | M06 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-007 | HM-SPLGT-01 | Spillway radial gate 8x6 m | Hydromechanical | 3 | EA | 510000 | ISGEC Heavy Engineering | 365 | 2026-02-15 | M04 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-008 | HM-SPLHST-01 | Spillway gate rope drum hoist 2x80 t | Hydromechanical | 3 | EA | 148000 | ISGEC Heavy Engineering | 300 | 2026-02-15 | M04 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-009 | HM-TRSTOP-01 | Tailrace stop log set 3 panels | Hydromechanical | 1 | SET | 92000 | Texmaco Rail | 180 | 2027-09-01 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-HM-010 | HM-TRC-MACH | Trash rack cleaning machine | Hydromechanical | 1 | EA | 220000 | SLP Industries | 300 | 2026-11-01 | M07 | spec_missing
northwind | HYD-MAHADEV-220 | HYD-TG-001 | TG-RUNNER-01 | Francis turbine runner 5.2 m dia 110 MW | Turbine | 2 | EA | 2850000 | Andritz Hydro | 540 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-002 | TG-WICKET-01 | Wicket gate assembly 24 vanes | Turbine | 2 | SET | 1180000 | Andritz Hydro | 420 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-003 | TG-SPIRAL-01 | Spiral case fabricated steel | Turbine | 2 | EA | 1620000 | Andritz Hydro | 420 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-004 | TG-DRAFT-01 | Draft tube liner stainless | Turbine | 2 | SET | 640000 | Andritz Hydro | 365 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-005 | TG-TOP-COV | Top cover and main shaft assy | Turbine | 2 | SET | 820000 | Andritz Hydro | 420 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-006 | TG-GOV-01 | Digital speed governor with hydraulic PU | Turbine | 2 | EA | 485000 | Voith Hydro Shanghai | 240 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-007 | TG-SERVO-01 | Wicket gate servo motor | Turbine | 4 | EA | 128000 | Voith Hydro Shanghai | 210 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-008 | TG-STAY-01 | Stay ring fabricated | Turbine | 2 | EA | 720000 | Andritz Hydro | 365 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-009 | TG-MIV-01 | Inlet butterfly valve 4.5 m bidir | Turbine | 2 | EA | 1280000 | Voith Hydro Shanghai | 365 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-TG-010 | TG-SHFTSL-01 | Shaft seal main labyrinth set | Turbine | 2 | SET | 68000 | Andritz Hydro | 180 | 2026-11-15 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-GE-001 | GE-STATOR-01 | Generator stator 110 MW 13.8 kV 50 Hz | Generator | 2 | EA | 3950000 | BHEL Hyderabad | 540 | 2027-01-15 | M08 | planned
northwind | HYD-MAHADEV-220 | HYD-GE-002 | GE-ROTOR-01 | Generator rotor with poles 110 MW | Generator | 2 | EA | 3120000 | BHEL Hyderabad | 540 | 2027-01-15 | M08 | planned
northwind | HYD-MAHADEV-220 | HYD-GE-003 | GE-EXC-01 | Brushless excitation system AVR | Generator | 2 | SET | 395000 | Siemens Energy | 300 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-GE-004 | GE-SLIPRG-01 | Slip rings and brush gear | Generator | 2 | SET | 82000 | BHEL Hyderabad | 210 | 2027-01-15 | M08 | planned
northwind | HYD-MAHADEV-220 | HYD-GE-005 | GE-COOL-01 | Generator air cooler bank | Generator | 2 | SET | 310000 | BHEL Hyderabad | 240 | 2027-01-15 | M08 | planned
northwind | HYD-MAHADEV-220 | HYD-GE-006 | GE-BRG-01 | Generator thrust and guide bearing set | Generator | 2 | SET | 440000 | BHEL Hyderabad | 300 | 2027-01-15 | M08 | spec_missing
northwind | HYD-MAHADEV-220 | HYD-TR-001 | TR-GT-130MVA | Generator transformer 130 MVA 13.8/220 kV | Transformer | 2 | EA | 2150000 | BHEL Bhopal | 450 | 2027-04-15 | M09 | planned
northwind | HYD-MAHADEV-220 | HYD-TR-002 | TR-SST-2MVA | Station service transformer 2 MVA 13.8/0.415 kV | Transformer | 2 | EA | 128000 | CG Power | 180 | 2027-05-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-TR-003 | TR-AUX-1MVA | Auxiliary transformer 1.5 MVA dry-type | Transformer | 1 | EA | 98000 | CG Power | 150 | 2027-05-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-TR-004 | TR-FIRE-DEL | Transformer water deluge fire system | Transformer | 2 | SET | 72000 | HD Fire Protect | 180 | 2027-05-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-GIS-001 | GIS-220-BAY | 220 kV GIS bay (CB+ISO+ES+CT+VT) | GIS Switchgear | 4 | EA | 895000 | Hitachi Energy | 360 | 2027-05-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-GIS-002 | GIS-220-SA | 220 kV gapless surge arrester | GIS Switchgear | 6 | EA | 18500 | Hitachi Energy | 240 | 2027-05-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-GIS-003 | GIS-220-CET | 220 kV cable end termination | GIS Switchgear | 4 | SET | 82000 | Prysmian | 300 | 2027-05-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-SG-001 | SG-13-UNIT | 13.8 kV unit switchgear lineup | Switchgear | 2 | EA | 485000 | ABB India | 240 | 2027-01-15 | M08 | planned
northwind | HYD-MAHADEV-220 | HYD-SG-002 | SG-415-MCC | 415 V motor control centre | Switchgear | 4 | EA | 118000 | Schneider Electric | 180 | 2026-12-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-SG-003 | SG-415-EMCC | 415 V emergency MCC with ATS | Switchgear | 2 | EA | 148000 | Schneider Electric | 180 | 2027-04-15 |  | planned
northwind | HYD-MAHADEV-220 | HYD-IPB-001 | IPB-13-6KA | Isolated phase bus 13.8 kV 6000 A | Bus Duct | 2 | SET | 520000 | CG Power | 300 | 2027-04-15 | M09 | planned
northwind | HYD-MAHADEV-220 | HYD-CB-001 | CB-220XLPE | 220 kV XLPE single core cable | Cables | 600 | M | 425 | Prysmian | 240 | 2027-04-15 | M10 | planned
northwind | HYD-MAHADEV-220 | HYD-CB-002 | CB-13-MV | 13.8 kV power cable 3C 240 sq.mm | Cables | 4500 | M | 72 | Polycab | 150 | 2026-11-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-CB-003 | CB-1-LT | 1.1 kV power cable 3.5C 300 sq.mm | Cables | 18000 | M | 28 | Polycab | 120 | 2026-12-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-CB-004 | CB-CTL-MC | Control cable 16C 1.5 sq.mm | Cables | 12000 | M | 8.5 | KEI Industries | 90 | 2027-01-01 |  | spec_missing
northwind | HYD-MAHADEV-220 | HYD-CB-005 | CB-INST-PR | Instrumentation cable shielded pair | Cables | 8000 | M | 11 | KEI Industries | 90 | 2027-02-01 |  | spec_missing
northwind | HYD-MAHADEV-220 | HYD-CB-006 | CB-FO-SM | Single-mode armoured fibre 24 core | Cables | 6000 | M | 14 | Polycab | 120 | 2027-03-01 |  | spec_missing
northwind | HYD-MAHADEV-220 | HYD-CB-007 | CB-TRAY-GI | Cable tray galvanized 600 mm wide | Cables | 3500 | M | 68 | Havells Cables | 90 | 2026-10-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-CI-001 | CI-DCS-PLT | Plant DCS turbine plus BOP redundant | C&I | 1 | SYS | 985000 | Emerson Process | 240 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-CI-002 | CI-PROT-GEN | Generator protection panel numerical | C&I | 2 | SET | 210000 | ABB India | 240 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-CI-003 | CI-VIB-MON | Vibration monitoring turbine generator | C&I | 2 | SET | 98000 | Emerson Process | 180 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-CI-004 | CI-SYNC-PNL | Synchronizing and metering panel | C&I | 2 | SET | 85000 | Schneider Electric | 180 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-CI-005 | CI-SCADA-RTU | SCADA RTU and gateway redundant | C&I | 1 | SET | 165000 | Emerson Process | 180 | 2027-09-15 | M11 | spec_missing
northwind | HYD-MAHADEV-220 | HYD-CI-006 | CI-FLD-INST | Field instruments RTD PT LT lot | C&I | 1 | LOT | 128000 | Endress+Hauser | 150 | 2027-06-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-CI-007 | CI-RES-LVL | Reservoir water level radar | C&I | 2 | EA | 18500 | Endress+Hauser | 120 | 2026-08-01 | M06 | planned
northwind | HYD-MAHADEV-220 | HYD-CI-008 | CI-TW-LVL | Tailwater level sensor pressure | C&I | 2 | EA | 9800 | Endress+Hauser | 90 | 2026-08-01 | M06 | planned
northwind | HYD-MAHADEV-220 | HYD-CW-001 | CW-PUMP-VT | CW pump vertical turbine 5 m3/s | Cooling Water | 4 | EA | 165000 | Kirloskar Brothers | 240 | 2027-04-15 | M09 | planned
northwind | HYD-MAHADEV-220 | HYD-CW-002 | CW-HX-PLATE | CW plate heat exchanger | Cooling Water | 4 | EA | 82000 | Kirloskar Brothers | 180 | 2027-04-15 | M09 | planned
northwind | HYD-MAHADEV-220 | HYD-CW-003 | CW-STR-AUTO | CW auto-clean strainer | Cooling Water | 4 | EA | 38000 | Kirloskar Brothers | 150 | 2027-03-15 |  | planned
northwind | HYD-MAHADEV-220 | HYD-CW-004 | CW-PIPE-DN6 | CW piping carbon steel DN 600 | Cooling Water | 220 | M | 520 | Jindal SAW | 120 | 2027-03-15 |  | planned
northwind | HYD-MAHADEV-220 | HYD-LS-001 | LS-OIL-COND | Turbine oil tank with conditioning unit | Lubrication | 2 | SET | 98000 | Voith Hydro Shanghai | 180 | 2027-06-01 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-CR-001 | CR-EOT-PWR | Powerhouse EOT crane 200/30 t double girder | Cranes | 1 | EA | 1280000 | Konecranes | 300 | 2026-11-01 | M07 | planned
northwind | HYD-MAHADEV-220 | HYD-CR-002 | CR-INT-BRG | Intake bridge crane 50 t single girder | Cranes | 1 | EA | 485000 | Demag Cranes | 240 | 2025-12-01 | M03 | planned
northwind | HYD-MAHADEV-220 | HYD-FP-001 | FP-CO2-GEN | Generator high pressure CO2 fire system | Fire Protection | 2 | SET | 148000 | HD Fire Protect | 180 | 2027-08-15 | M11 | planned
northwind | HYD-MAHADEV-220 | HYD-FP-002 | FP-DEL-TR | Transformer water deluge skid | Fire Protection | 2 | SET | 72000 | HD Fire Protect | 150 | 2027-05-15 | M10 | spec_missing
northwind | HYD-MAHADEV-220 | HYD-FP-003 | FP-FDA-PNL | Fire detection and alarm system | Fire Protection | 1 | SYS | 128000 | Tyco Fire Protection | 180 | 2027-06-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-HV-001 | HV-PH-AHU | Powerhouse HVAC AHU and ductwork | HVAC | 1 | SYS | 310000 | Voltas | 180 | 2027-04-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-HV-002 | HV-SG-PAC | Switchgear room precision AC 18 TR | HVAC | 2 | SET | 72000 | Blue Star | 150 | 2027-04-01 |  | planned
northwind | HYD-MAHADEV-220 | HYD-CV-001 | CV-CEM-OPC | OPC 53 grade cement bulk | Civil | 28000 | T | 98 | UltraTech Cement | 30 | 2026-01-15 | M04 | planned
northwind | HYD-MAHADEV-220 | HYD-CV-002 | CV-CEM-PPC | PPC cement bulk | Civil | 12000 | T | 88 | Ambuja Cements | 30 | 2026-01-15 | M04 | planned
northwind | HYD-MAHADEV-220 | HYD-CV-003 | CV-REBAR-550 | TMT rebar Fe 550 8 to 32 mm | Civil | 6500 | T | 720 | Tata Steel | 60 | 2026-02-15 | M04 | planned
northwind | HYD-MAHADEV-220 | HYD-CV-004 | CV-STRUCT-ST | Structural steel plates and sections | Civil | 2400 | T | 1180 | JSW Steel | 90 | 2026-04-01 | M05 | planned
northwind | HYD-MAHADEV-220 | HYD-CV-005 | CV-FLY-ASH | Class F fly ash bulk | Civil | 4800 | T | 42 | ACC Limited | 30 | 2026-01-15 | M04 | planned
northwind | HYD-MAHADEV-220 | HYD-CV-006 | CV-WP-MEM | Bituminous waterproofing membrane | Civil | 12000 | M2 | 18 | Fosroc | 60 | 2026-03-01 | M04 | spec_missing
northwind | PRJ-NW-STEEL | PRJ-NW-STEEL-001 | ROLL-STAND-6H | 6-high cold rolling stand | Heavy machinery | 4 | EA | 3900000 | ThyssenKrupp Specialty Plate | 360 | 2026-11-18 | M2 | planned
northwind | PRJ-NW-STEEL | PRJ-NW-STEEL-002 | REHEAT-FURN | Walking-beam reheat furnace | Furnace | 1 | EA | 6200000 |  | 330 | 2026-11-03 | M2 | spec_missing
northwind | PRJ-NW-STEEL | PRJ-NW-STEEL-003 | COILER-DOWN | Downcoiler assembly | Heavy machinery | 2 | EA | 2100000 | Voith Industrial Services | 280 | 2026-10-09 | M3 | planned
northwind | PRJ-NW-STEEL | PRJ-NW-STEEL-004 | DRIVE-MV | MV variable-speed mill drive | Automation | 8 | EA | 480000 | Bharat Heavy Electricals | 210 | 2026-09-04 | M3 | planned
northwind | PRJ-NW-STEEL | PRJ-NW-STEEL-005 | WORKROLL-FORGED | Forged work roll set | Alloy plate | 24 | EA | 95000 | ThyssenKrupp Specialty Plate | 150 | 2026-08-05 | M3 | planned
northwind | PRJ-NW-CEMENT | PRJ-NW-CEMENT-001 | KILN-5000TPD | Rotary kiln 5000 TPD | Heavy machinery | 1 | EA | 8400000 |  | 390 | 2026-12-03 | M2 | spec_missing
northwind | PRJ-NW-CEMENT | PRJ-NW-CEMENT-002 | VRM-RAW | Vertical raw mill | Heavy machinery | 1 | EA | 4600000 | Voith Industrial Services | 330 | 2026-11-03 | M2 | planned
northwind | PRJ-NW-CEMENT | PRJ-NW-CEMENT-003 | PREHEAT-TWR | 5-stage preheater tower | Process | 1 | EA | 3700000 |  | 300 | 2026-10-19 | M2 | spec_missing
northwind | PRJ-NW-CEMENT | PRJ-NW-CEMENT-004 | CLINKER-COOL | Grate clinker cooler | Process | 1 | EA | 2400000 | ThyssenKrupp Specialty Plate | 240 | 2026-09-19 | M3 | planned
northwind | PRJ-NW-CEMENT | PRJ-NW-CEMENT-005 | BAGHOUSE-PULSE | Pulse-jet baghouse filter | Environmental | 2 | EA | 680000 | Bharat Heavy Electricals | 120 | 2026-07-21 | M3 | planned
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-001 | RUNNER-REFURB | Francis runner refurbishment | Hydro turbines | 1 | EA | 1900000 | Andritz Hydro | 300 | 2026-08-30 | M2 | delivered
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-002 | GEN-REWIND | Generator stator rewind | Generators | 1 | EA | 1450000 | Bharat Heavy Electricals | 270 | 2026-07-31 | M3 | delivered
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-003 | WICKET-GATE | Wicket gate assembly set | Hydro turbines | 24 | EA | 48000 | Andritz Hydro | 180 | 2026-05-02 | M3 | delivered
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-004 | DRAFT-TUBE-LIN | Draft tube liner plate | Alloy plate | 60 | T | 2400 | ThyssenKrupp Specialty Plate | 120 | 2026-03-03 | M3 | delivered
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-005 | GOV-HYDRAULIC | Digital governor + hydraulics | Automation | 1 | LOT | 620000 | Voith Industrial Services | 150 | 2026-04-02 | M3 | delivered
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-006 | XFMR-GEN-90 | Generator transformer 90 MVA | Electrical | 1 | EA | 540000 | Bharat Heavy Electricals | 240 | 2026-07-01 | M4 | ordered
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-007 | PENSTOCK-LINER | Penstock liner segments | Penstock fabrication | 8 | EA | 210000 | Voith Industrial Services | 210 | 2026-06-01 | M4 | spec_missing
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-008 | EXCITER-STATIC | Static excitation system | Automation | 1 | EA | 380000 |  | 120 | 2026-03-03 | M4 | spec_missing
northwind | PRJ-NW-KAVI | PRJ-NW-KAVI-009 | COOLING-WTR-PMP | Cooling water pump set | Rotating equipment | 2 | EA | 145000 | Voith Industrial Services | 90 | 2026-02-01 | M5 | spec_missing

## Vendors
VENDORS
Vendor Scorecards
Tenant | Vendor | Category | Country | Score | Grade | OTD % | Quality PPM | Annual spend $ | Flags | Single-source
arcforge | Mitsuba Automation | PLC and control panels | Japan | 95 | A | 96 | 420 | 320000 | 0
arcforge | Copperline Metals | Copper busbars | Malaysia | 94 | A | 97 | 300 | 510000 | 0
arcforge | Polaris Forging (test) | Forged valves | India | 93 | A | 95.5 | 380 | 240000 | 1
arcforge | Delhi Metals Co | Copper busbars | India | 89 | B | 94 | 520 | 210000 | 1
arcforge | BluePeak Controls | PLC and control panels | Germany | 83 | B | 93 | 650 | 1280000 | 1
arcforge | Kerala Forge Works | Forged valves | India | 81 | B | 91 | 1400 | 180000 | 1
arcforge | Helios Cast & Forge | Forged valves | India | 66 | C | 88 | 1800 | 740000 | 2 | yes
helios | Coastline Marine Coatings | Marine epoxy | Netherlands | 93 | A | 95 | 280 | 240000 | 0
helios | NorthCable Subsea | Subsea cables | Norway | 84 | B | 92 | 410 | 4200000 | 1
helios | DeepDive ROV Systems | ROV connectors | UK | 73 | C | 89 | 820 | 860000 | 2 | yes
helios | Aberdeen Steel Fab | Offshore structural | UK | 72 | C | 86 | 1100 | 2900000 | 1
northwind | ThyssenKrupp Specialty Plate | Alloy plate | Germany | 89 | B | 92 | 320 | 1500000 | 0
northwind | Voith Industrial Services | Penstock fabrication | Germany | 84 | B | 91 | 410 | 2200000 | 1
northwind | Bharat Heavy Electricals | Generators | India | 80 | B | 88 | 520 | 4100000 | 1
northwind | Andritz Hydro | Hydro turbines | Austria | 78 | B | 94 | 180 | 6800000 | 2 | yes

## Concentration
VENDORS
Category Concentration
Tenant | Category | # Vendors | Total spend $ | Top vendor | Top share % | Single-source
arcforge | PLC and control panels | 2 | 1600000 | BluePeak Controls | 80
arcforge | Forged valves | 3 | 1160000 | Helios Cast & Forge | 63.8
arcforge | Copper busbars | 2 | 720000 | Copperline Metals | 70.8
helios | Subsea cables | 1 | 4200000 | NorthCable Subsea | 100 | yes
helios | Offshore structural | 1 | 2900000 | Aberdeen Steel Fab | 100 | yes
helios | ROV connectors | 1 | 860000 | DeepDive ROV Systems | 100 | yes
helios | Marine epoxy | 1 | 240000 | Coastline Marine Coatings | 100 | yes
northwind | Hydro turbines | 1 | 6800000 | Andritz Hydro | 100 | yes
northwind | Generators | 1 | 4100000 | Bharat Heavy Electricals | 100 | yes
northwind | Penstock fabrication | 1 | 2200000 | Voith Industrial Services | 100 | yes
northwind | Alloy plate | 1 | 1500000 | ThyssenKrupp Specialty Plate | 100 | yes

## PRs
SOURCING
Purchase Requisitions
Tenant | PR No | Project | Code | Qty | UoM | Budget $ | Buyer | Strategy | Status | RFQ | PO
arcforge | PR-00002 | PRJ-RB-660 | BFP-660-A | 2 | EA | 1840000 | Unassigned | multi_source | rfq_issued | RFQ-00002
arcforge | PR-00001 | PRJ-RB-660 | VALVE-16-A105 | 30 | EA | 115500 | K. Menon | multi_source | po_created | RFQ-00001 | SPO-00001

## POs
SOURCING
Sourcing Purchase Orders
Tenant | PO No | Project | Code | Vendor | Qty | Value $ | Incoterm | Lead (d) | Status
arcforge | SPO-00001 | PRJ-RB-660 | VALVE-16-A105 | Helios Cast & Forge | 30 | 113400 | CIP | 44 | draft

## Commercial
COMMERCIAL
Commercial Roll-up
Tenant | Project | Lines | Budget $ | Quoted $ | Awarded $ | Savings $ | Variance % | Over-budget lines
arcforge | Riverbank 2x660 MW Power Plant | 2 | 1955500 | 113400 | 113400 | 2100 | -94.2 | 0

## Approvals
GOVERNANCE
Approvals Queue
Tenant | ID | Kind | Title | Status | Requested by | Decided by | Result ref
arcforge | APR-0005 | quote_above_budget | Over-budget quote · BFP-660-A | pending | Arcforge Senior Buyer
arcforge | APR-0004 | award_single_source | Award VALVE-16-A105 to Helios Cast & Forge | approved | Arcforge Senior Buyer | Arcforge Procurement Head | SPO-00001
arcforge | APR-0003 | award_single_source | Award VALVE-16-A105 to Helios Cast & Forge | pending | Arcforge Senior Buyer
arcforge | APR-0002 | award_single_source | Award VALVE-16-A105 to Helios Cast & Forge | pending | Arcforge Senior Buyer
arcforge | APR-0001 | award_single_source | Award VALVE-16-A105 to Helios Cast & Forge | pending | Arcforge Senior Buyer

## Alerts
MONITOR
Live Alert Feed
Tenant | Severity | Category | Title | Detail
arcforge | critical | schedule | M3 Bulk material on site — Meridian 2x350 MW CCGT — Unit 1 Execution | Required on site in 3d
arcforge | critical | expediting | Escalate PO-AF-24017 · Helios Cast & Forge | 95% slip probability, 7d expected slip
arcforge | high | approval | Approval needed: Over-budget quote · BFP-660-A | Copperline Metals quoted $3,680,000 vs $1,840,000 budget (+100%) on BFP-660-A
arcforge | high | approval | Approval needed: Award VALVE-16-A105 to Helios Cast & Forge | Award overrides the comparison winner · $113,400 · VALVE-16-A105 (RFQ-00001)
arcforge | high | approval | Approval needed: Award VALVE-16-A105 to Helios Cast & Forge | Award overrides the comparison winner · $113,400 · VALVE-16-A105 (RFQ-00001)
arcforge | high | approval | Approval needed: Award VALVE-16-A105 to Helios Cast & Forge | Award overrides the comparison winner · $113,400 · VALVE-16-A105 (RFQ-00001)
arcforge | high | schedule | M1 Engineering freeze — Riverbank 2x660 MW Power Plant | Required on site in 13d
arcforge | medium | vendor | Single-source exposure: Helios Cast & Forge | Forged valves · no approved alternative · $740,000 annual spend
arcforge | medium | engineering | 1 BOM line(s) missing specs on near-term milestones | Issue spec requests to engineering to protect the procurement runway.
helios | critical | schedule | M3 Bulk material on site — Valhall Bravo Platform Tie-In | Required on site in 3d
helios | critical | expediting | Escalate PO-HE-31108 · DeepDive ROV Systems | 91% slip probability, 6d expected slip
helios | medium | vendor | Single-source exposure: DeepDive ROV Systems | ROV connectors · no approved alternative · $860,000 annual spend
northwind | critical | schedule | M3 Bulk material on site — Kavi Hydro Unit 3 Major Overhaul | Required on site in 3d
northwind | medium | vendor | Single-source exposure: Andritz Hydro | Hydro turbines · no approved alternative · $6,800,000 annual spend